Guiding Principles

- Analyze what has already been done/learned before conducting additional research

- Refrain from conducting more primary research until marketing goals and success metrics are specified

- Specify how research will be linked to marketing goals/decisions and success metrics before it is conducted

Research Objectives

- Identify what consumers believe are conservation and energy efficiency behaviors

- Determine what motivates consumers to be more energy efficient

| Objective | Methodology | Estimated Budget | Time Required |
| --- | --- | --- | --- |
| Phase 1: Secondary Research |  |  |  |
| 1. Summarize What We Know About the NW Population, including: - Energy efficiency and other environmental attitudes & behaviors - Identify size and characteristics of various behavioral and demographic segments - Hypothesize likely motivators for/approaches to behavior change | Compile/analyze/summarize data from existing studies (specifically, segmentation studies from PSE, BPA, Snohomish PUD, Energy Trust of OR, BC Hydro, Ontario Power Authority) | $25K - $50K (depends on amount of analysis) | 8 – 12 weeks (could be done concurrently with tasks 2 and 3) |
| 2. Summarize What’s Been Done/Learned from Key Energy Efficiency/Global Warming Behavior Change efforts, including: - Energy efficiency behavior change efforts/campaigns to date (e.g., Avista “Every Little Bit”, CA “Flex Your Power,” CT “One Thing,” Northeast’s “Start Small Save Big,” Gore’s “We” campaign) - Compile lessons learned/ideas from the above efforts - Identify success metrics from campaigns | Secondary research + interviews | $25-50K (depends on amount of analysis) | 8 – 12 weeks (could be done concurrently with tasks 1 and 3) |
| 3. Summarize What’s Been Done/Learned from Other Relevant Efforts (Non-energy Related) - Identify and compile summary of effective behavior change efforts outside of the energy efficiency field (e.g., anti-littering; recycling, preventive health) - Summarize lessons learned/ideas from the above efforts | Secondary research | $25-50K (depends on amount of analysis) | 8 – 12 weeks (could be done concurrently with tasks 1 and 2) |

| Phase 2: Primary Research—Exploratory |  |  |  |
| --- | --- | --- | --- |
| 4. Explore strategies for how to get customers who have already acted to do more / explore strategies for reaching and motivating customers who have not done energy efficiency - How to reach them/what will get their attention in this “green” world - What will motivate them (even if they don’t know it, like normative behavior) - What will change what they do/increase what they do - Who are the most effective “messengers” and situations for success (i.e., under what circumstances do people learn the best, change the most) | TBD, but may include: focus groups, ethnographic research, experimental research or applied experiments to test behavioral economics concepts like choice order, opt-in/opt out strategies, the power of free, normative behavior | $50K - $150K (depending on number of groups and locations: $50K for 6-7 groups in 2-3 cities) | 3 – 6 months |
| Phase 3: Primary Research—Conclusive |  |  |  |
| 5. Identify most compelling messaging by key behavioral/ demographic segment; quantify baseline levels of key success metrics (e.g., awareness, perceptions, behaviors) | Regional quantitative survey | $150K | 8 – 12 weeks |
| 6. Test specific “delivery approaches” (e.g., copy, creative executions, “messengers”) | TBD, but may include: focus groups, quantitative copy testing and experimental test approaches as above | $50K - $150K (depending on number of groups and locations: $50K for 6-7 groups in 2-3 cities) | 3 – 6 months |
| 7. Track key success metrics over time | Regional quantitative survey | $150K+ every 1-2 yrs | 8-12 weeks |
| 8. Repeat segmentation | Regional quantitative survey | $200 - $300K every 3-5 years | 3 – 4 months |

Outstanding Questions: Limit to residential consumers or add in business, institutional customers?  There are many links among these groups that need exploring.  In addition, business/institutions might sponsor research, implementation.

- Will research only target consumers?

- Do we include business/institutions?

- What about other stakeholder groups, like policy makers?